## Sheet1
Michael | Josh | Keith | Simon | Glyn
Who did the work? | what task? | No of hours | Date
Simon | Risk Register Organisational Risks | 0.8 | 2018-08-19
Glyn | Project Plan | 0.6 | 2018-08-22
Glyn | Project Plan, Proof reading and editing of Analysis of Alternatives and Risk Assesment | 2 | 2018-08-24
Keith | process management, task allocation, progress tracking | 2 | 2018-08-21
Keith | Roles and responsibilities | 0.5 | 2018-08-23
Micheal | Analysis of Alternatives, Proof reading and editing of PMP and Analysis of alternatives | 3.5 | 2018-08-24
Josh | Risk Register, Coding interface testing | 3 | 2018-08-23